## Description
COMP 3000 -- Object Oriented Programming
Iteration: | 1
Objective: | To create a chemical database and stock system using the command line.
Product: | Chemical Database
Deliverables: | Via Canvas: | Include this spreadsheet with completed process information with your Canvas submission.
| Via GitHub: | https://github.com/rgo0004/COMP3000SemesterProject
Notes on Process: | - Follow the process in the "Process" worksheet based on your own project.
- Ensure you follow the course coding and counting standards.
- Be honest in your data. Your grade depends on how you follow the process and the quality of your work, not on the speed of your work or the number of defects found.
- Below are clarifications for process worksheets that have been problematic in the past:
|  | Worksheet | Special Instructions
|  | Plan | Record lines of code for production code only. Do not include test code.
|  | Acceptance | Develop acceptance tests for the specified black box. Do not include tests for items that are not part of the specifications (meaning, items over and above the specs -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance. Actual results should reflect the state of the software at the time of delivery.
|  | Time Log | Use the "sandbox" activity to record time spent experimenting with the assignment requirements.
|  | Change Log | The "Reference to a Previous Change" column allows you to indicate that you are fixing a fix. The value in the column should be the number on the change log of the fix you are repairing.
|  | Historical Data | Record your process and product data from all previous programming assignments. Do this as part of the planning activity.
|  | Review | During the planning activity, list a count of all defects that you've previously encountered. Construct a checklist from your defect logs. Indicate during the review activity the number of times the review checklist item found an error.
|  | Scenarios | Create an interface specification depicting the interaction between a test driver and the class specified above. Create nominal scenario(s) and anomalous scenario(s) sufficient to convey your understanding of software behavior
|  | Lessons Learned | This tab is optional. Use it to record great ideas, suggestions, etc. Whining is not productive :)
|  | Architecture | Develop CRC cards only for the production code needed to implement the specifications. Do not include CRC cards for test drivers.
|  | Estimate | Record all the items from your architecture. Do not include test code.
|  | Iterations | Record the number of iterations you plan to use, together with the planned velocity of each iteration. Record the amount of time you plan to have available each day of the project window. Please plan for more than one iteration.
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, select the protected worksheet, select Tools -> Protection -> unprotect.

## Process
Constants |  |  |  | 0
Start date: | 36526 |  | Grades: | 1
End date: | 73051 |  |  | 0.95
Phases: | Analyze | Identifying customer needs |  | 0.9
| Architect | High-level design |  | 0.85
| Plan project | Determine actions/effort for project duration |  | 0.8
| Plan iteration | Determine actions/effort this iteration |  | 0.75
| Construct | Low-level design, coding, unit testing |  | 0.7
| Refactor | Restructure internal design |  | 0.65
| Review | Examine test code for risk mitigation |  | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | did not follow
| Requirements Clarification | Clarifications to requirements |  | very painful
| Product syntax | Syntax flaws in the deliverable product |  | painful
| Product logic | Logic flaws in the deliverable product |  | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | very helpful
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 0
Y/N: | Yes |  |  | 0
| No |  |  | 0
Proxy Types: | - |  |  | Base
| Calculation |  |  | New
| Data |  |  | Reusable
I/O
Logic
Sizes: | VS | S | M | VL
upper | -1.5 | -0.5 | 0.5 | 99999
mid | -2 | -1 | 0 | 2
lower | 0 | -1.5 | -0.5 | 1.5
| 0 | 0 | 0
<-- Mandatory |  | ✔
Process Script
Minimal Guiding Indicators |  |  |  | Minimal Sufficient Activities
| Goal | Indicator |  |  | Engineering Activities
| Cost: | None |  |  | Envision
| Schedule: | On time |  |  | Analyze
| Performance: |  |  |  | Synthesize
| Product: |  |  |  | Architecture
| NFR: | None |  |  | Articulate
| FR: | Equivalence Class Partitioning |  |  | Construct
| Process: | Completed spreadsheet |  |  | Interpret
Integration Test
Operational Activities
Plan
Plan project
Monitor/Control
Post Mortem
Release
Minimal Viable Process |  |  |  | Minimal Effective Practices
|  |  |  | MSA | MEP | Spreadsheet tab on which to document MEP
|  |  |  | Analyze | • Write as many acceptance tests as you feel are necessary to understand the assignment | Acceptance
|  |  |  | Architect | • Create CRC cards for each component you plan to build/modify | Architecture
|  |  |  | Plan Project | • Transfer process information from previous assignment | Historical Data
[5 empty] | • Analyze past defects and develop code review checklist | Review
[5 empty] | • Guess projected LOC | Plan
[5 empty] | • Guess projected effort (in minutes) | Plan
|  |  |  | Construction | • Repeat
• • Select/write a test case
[5 empty] | • • Run the test a red light test | Acceptance (if test is an acceptance test)
• • While the test is not red
• • • Diagnose why the test was not red
• • • If the problem was due to incorrect test code
[5 empty] | • • • • Fix the defect and log it in the change log | Change Log
• • • • Run the test as a red light test
• • • Else
• • • • Continue to the next red light test
• • Build enough production code to make the test pass
• • Run the test as a green light test
• • While the test is not green
[5 empty] | • • • Fix the defect and log it in the change log | Change Log
• • • Run the test as a green light test
• • Clean up the code as appropriate and run as blue light
• Until test coverage is sufficient and all tests pass
• Commit all code to git
|  |  |  | Review | • Perform rubber duck review of test code | Review, Change Log
|  |  |  | Refactor | • Refactor production code to remove odious smells; run as blue light | Change Log
|  |  |  | Post Mortem | • Record acceptance test results | Acceptance
[5 empty] | • Count production LOC | Plan
[5 empty] | • Record lessons learned (optional) | Lessons
|  |  |  | Release | • Commit all code to git
• Push to GitHub.com
• Upload spreadsheet to Canvas
Minimal Guiding Indicators
Cost: |  | - |  | Monitor | • Record time spent in each activity. | Time Log
Schedule: |  | Submitted on time |  |  | • Record defects, changes to requirements. | Change Log
Performance:
Product:
| NFR: | Meets delivery requirements.
| FR: | Boundary Value Analysis
| Process: | Evident on spreadsheet
Operational Engineering
Plan Project
Post Mortem
Release
Monitor
Construct
Not all components are constructed
Analyze
Review
Refactor
Failed review
Architect

## Spec Notes (hidden)
Specification Notes

## Assessment
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Assessment Worksheet
Name: |  | Graham Oliver
User name: |  | rgo0004
GitHub user name: |  | rgo0004
https://github.com/rgo0004/COMP3000SemesterProject
Instructor Assessment
Product Assessment
Process Assessment:
Score: |  | out of | 100
Quality checks |  |  | changes from the previous assignment are in red
General
Are all regions highlighted in yellow appropriately complete?
Does the workbook reflect a faithful record of information?
Has this assignment been uploaded as specified by the assignment description?
Project Plan Summary
Was the planned information determined before development and not altered after development?
Is planned time expressed in minutes?
Do LOC counts address production code (and exclude test code)?
Is the actual line count calculated according to the counting standard?
Time Recording Log
Does the log reflect a faithful record of time spent?
Do no times span midnight?
Does the log reflect the activities in the specified process?
Is post mortem the final phase?
Does the time recording log reflect the your lifecycle?
Change Log
Is each change accompanied by a description in the "comment" field?
Are changes recorded against the appropriate phase in which they were injected and removed?
Does the "removed" count equal the "injected" count? If not, is the rational documented in the "lessons learned" tab?
Are the dates and times in the change log consistent with the dates and times in the time recording log?
Acceptance Report
Do actual results support expected results?
Do actual results marked as "Passed with issues" include a comment?
Source Code
Does the code reflect the coding standard?
Will the code compile without change?
Does the production code contain any packages that aren't part of the customer's production environment.
Does the code take into consideration specified error conditions?
Does the code fulfill the assignment requirements?
Does the code follow the prescribed directory format (i.e., prod, test, sandbox)?
Historical Data
Is the historical data complete?
Have previously noted problems in process measurements been corrected?
Deliverables
Has the spreadsheet been uploaded to Canvas?
Has all the code been pushed to GitHub?
Is test code in a separate folder?
Will the test code work without modification?
Does the git respository reflect commits at the specified process points?
Does the "Assessment" tab include your name, your AU username, etc.
Review
Did you construct your review checklist during the planning phase?
Does the error count indicated the analysis of defects match your historical defect count?
Are checklist items answerable in "yes" or "no" terms?
Does your checklist reflect at least one common item from your defect log ?
Does your checklist contain more than contrived "mom and apple pie" items?
Refactor
Is code free of the following bad smells: duplicate code, long methods, long classes
temporary variables, useless comments, coding standard violations?
Scenario
Were the scenarios constructed during the analysis phase (and not changed later)?
Does each scenario describe as fully as possible the interaction with the software under construction?
Are the actors correctly identified?
Are suitably understandable examples given?
Are events and responses directly observable?
Architecture
Was the architecture determined before construction (and not changed later)?
Does the architecture reflect a solid initial understanding of the solution?
Does the architecture show all components required for the solution (with the exception of system built-in components)?
Are collaborators specified correctly?
Do functionally-decomposed components have only one operation? Has the operation been given the component name?
Are component operations given names to suggest their behavior?
Does the architecture exhibit "good" design characteristics, such as appropriate levels of coupling, cohesion, etc.?
Estimate
Does each component denoted by a CRC card appear in the estimate as either base code, new components, or reused code?
Is base code vs reuse code identified correctly?
Do the base components and the new comopnents reflect the architecture?
Are the base components and new components sized according to historical proxies?
Is a rationale provided if either the LOCp and/or Ep are overridden?
Does the value of LOCa reflect effort expended on creating, adding, or modifying production code?
Is actual LOC data recorded at post mortem time?
Iterations
Is more than one iteration planned?
Does the WBS list all iterations?
Is the overall estimate of time in the WBS consistent with the calculated effort?
Are the planned completion dates of iterations in the WBS consistent with the calendar?
Are planned times recorded from the start of the calendar through the end of the project?
Does the calendar corroborate the WBS, and visa versa?
Construction
Did you follow the design -> test(failure) -> code -> test(success) -> clean up (if necessary) -> repeat pattern?
Are all unit tests written so that passing the test satisifies requirements?
Are unit tests written to the level of boundary value analysis?
Is there at least one test suite which, when run, exercises the entire production code base?
Does your code pass all test cases?

## Historical Data
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
Historical Data
Current Assignment: |  | Assignment 6 | CAAssignment 6.xls
Immediate Past Assignment: |  | Assignment6 | 202110Assignment4
All previous
Program Size (LOC) |  | LOCp | LOCa | LOCa
Base code LOC count
Lines deleted from Base
Lines modified from Base
Lines added to Base
Reused lines
New lines of production code |  | 300 | 401 | 401
Component Count |  | Plan | Actual | Actual to Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
All previous
Time In Phase (minutes) |  | Ep | Ea | Ea | To Date %
Analyze |  |  | 60 |  | 0%
Architect |  |  | 180 |  | 0%
Plan project |  |  | 60 |  | 0%
Plan iteration |  |  | 30 |  | 0%
Construct |  |  | 600 |  | 0%
Refactor |  |  | 120 |  | 0%
Review |  |  | 120 |  | 0%
Integration test |  |  | 60 |  | 0%
Repattern |  |  | 60 |  | 0%
Postmortem |  |  | 120 |  | 0%
Sandbox |  |  | 60 |  | 0%
TOTAL |  |  | 1470 | 0 | 0%
All previous
Changes traced to the activities below: |  |  |  | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  | 2 |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  | 2 |  | 0%
Sandbox |  |  | 1 |  | 0%
TOTAL |  |  | 5 | 0 | 0%
App previous
Changes implemented in the activities below: |  |  |  | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
Size Matrix (LOC/Method)
| Lower | Mid | Upper
VS
S
M
L
VL
Project History
| New and Changed LOC |  |  | Effort
Project Name | Raw LOC | Planned LOC | Actual LOC | Estimated Time | Actual Time | LOCa/LOCr | Ea/LOCa
1.xls | 0 |  |  |  |  | 0 | 0
CA02 | 0 |  |  |  |  | 0 | 0
3.xls | [5 empty] | 0 | 0
CA04 | 0 |  |  |  |  | 0 | 0
CA05 |  | 300 | 401 | 0 | 1470 | 0 | 3.6658 | 4.9
Project Trends
Productivity= | #DIV/0! | LOC/hr
Average size= |  | LOC/method
Component History
Component Name |  | Total LOC | Method Count | Type | Size | LOC/method | ln(LOC/meth)
chemicalDatabase::showList |  | 7 |  | Logic | -
chemicalDatabase::getProperty |  | 61 |  | - | -
chemicalDatabase::addremove |  | 103 |  | - | - |  |  |  | `
chemicalDatabase::chemicalDatabase |  | 35 |  | - | -
chemicalDatabase::stockAccess |  | 15 |  | - | -
chemicalDatabase::vaporPressure |  | 37 |  | - | -
stockRoom::addremove |  | 72 |  | - | -
stockRoom::showStock |  | 11 |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
[6 empty] | Average= | 0
[6 empty] | Std= | 0
Note on C57: Estimate the number of new lines of code that provide new functionality to meet the specifications of this assignment.
Note on C61: Estimate of the number of previously-written components that require modification
Note on C62: Estimate of the number of entirely new components

## Review
Review
Standards
Start date: | 2000-01-01 |  | Grades: |  |  | AA
End date: | 2020-01-01 |  |  |  |  | A
Phases: | Analysis |  |  |  |  | AB
| Architecture |  |  |  |  | B
| Planning |  |  |  |  | BC
| Construction |  |  |  |  | C
| Refactoring |  |  |  |  | CD
| Review |  |  |  |  | D
| Integration Test |  |  |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration |  |  | NA
| Build |  |  |  |  | 1
| Product syntax |  |  |  |  | 2
| Product logic |  |  |  |  | 3
| Product interface |  |  |  |  | 4
| Product checking |  |  |  |  | 5
| Test syntax |  |  |  |  | 6
| Test logic |  |  |  |  | 7
| Test interface |  |  |  |  | 8
| Test checking |  |  |  |  | 9
| Bad Smell |  |  |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
Defect Pareto Analysis (taken from all defects to date)
| Type | Description |  | Count of Occurrences | %
| Requirements Change | Changes to requirements |  |  | 0%
| Requirements Clarification | Clarifications to requirements |  |  | 0%
| Product syntax | Syntax flaws in the deliverable product |  | 1 | 20%
| Product logic | Logic flaws in the deliverable product |  | 3 | 60%
| Product interface | Flaws in the interface of a component of the deliverable product |  |  | 0%
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  |  | 0%
| Test syntax | Syntax flaws in the test code |  |  | 0%
| Test logic | Logic flaws in the test code |  |  | 0%
| Test interface | Flaws in the interface of a component of the test code |  |  | 0%
| Test checking | Flaws with boundary/type checking within a component of the test code |  |  | 0%
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 1 | 20%
|  |  | Total | 5 | <-- Warning, defect count doesn't match Historical Data
Code Review Checklist
| Item |  |  | Number of times this item detected a defect during review
| chemicalDatabase::chemicalDatabase(): adds the 4 default chemicals to database |  |  | 0
| chemicalDatabase::getProperty(): allows user to retrieve properties |  |  | 1
| chemicalDatabase::stockAccess(): allows stockRoom::addremove to get info from database |  |  | 0
| chemicalDatabase::addremove(): allows user to add and remove chemicals from database |  |  | 1
| chemicalDatabase::vaporPressure(): allows user to enter a temperature and calculate vapor pressure |  |  | 2
| chemicalDatabase::showList(): shows all chemical names in database |  |  | 0
| stockRoom::showStock: shows stock of all chemicals in stockroom |  |  | 1
| stockRoom::saddremove: add or remove stock from stockroom |  |  | 3

## Acceptance
Constants | [5 empty] | 0
Start date: | 36526 |  |  | Grades: | AA | 1 | 0
End date: | 73051 |  |  |  | A | 0.95 | 0
Phases: | Analyze |  | Identifying customer needs |  | AB | 0.9 | 0
| Architect |  | High-level design |  | B | 0.85 | 0
| Plan project |  | Determine actions/effort for project duration |  | BC | 0.8 | 0
| Plan iteration |  | Determine actions/effort this iteration |  | C | 0.75 | 0
| Construct |  | Low-level design, coding, unit testing |  | CD | 0.7 | 45252
| Refactor |  | Restructure internal design |  | D | 0.65 | 45253
| Review |  | Examine test code for risk mitigation |  | F | 0.5 | 45254
| Integration test |  | End-to-end test of components to date |  |  |  | 45255
| Repattern |  | Restructure external design |  |  |  | 45256
| Postmortem |  | Capture post-development statistics |  |  |  | 45257
| Sandbox |  | Prove ideas, try concepts |  |  |  | 45258
45259
45260
45261
#REF!
Defect Types: | Requirements Change |  | Changes to requirements | Iteration | NA | did not follow | #REF!
| Requirements Clarification |  | Clarifications to requirements |  | 1 | very painful | #REF!
| Product syntax |  | Syntax flaws in the deliverable product |  | 2 | painful | #REF!
| Product logic |  | Logic flaws in the deliverable product |  | 3 | neutral | #REF!
| Product interface |  | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | #REF!
| Product checking |  | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | #REF!
| Test syntax |  | Syntax flaws in the test code |  | 6 |  | #REF!
| Test logic |  | Logic flaws in the test code |  | 7 |  | #REF!
| Test interface |  | Flaws in the interface of a component of the test code |  | 8 |  | #REF!
| Test checking |  | Flaws with boundary/type checking within a component of the test code |  | 9 |  | #REF!
| Bad Smell |  | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | #REF!
Y/N: | Yes |  |  |  | Passed | 0 | #REF!
| No |  |  |  | Passed with issues | 0 | 45275
Proxy Types: | - |  |  |  | Failed | Base | 45276
| Calculation |  |  |  | Not tested | New | 45277
| Data |  |  |  | Not applicable | Reusable | 45278
| I/O | [5 empty] | 45279
| Logic | [5 empty] | 45280
45281
Sizes: | VS |  | S | M | L | VL | VS
upper | -1.5 |  | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 |  | -1 | 0 | 1 | 2 | M
lower | 0 |  | -1.5 | -0.5 | 0.5 | 1.5 | L
| 0 |  | 0 | 0 | 0 |  | VL
Acceptance Test Report
Use this worksheet to record tests that, if passed, tell you that your software is complete. It is not a chronology, so do not list a history of tests. List only tests that are directly linked to requirements (in other words, do not list tests for methods or components that you create over and above what is required to fulfill the specified interface definition -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance.
Requirements:
#REF!
#REF!
#REF!
#REF!
#REF!
Requirement | Test Description | Test | Expected Results |  | Actual Results | Issues
Requirement | Ability to add and remove chemicals, and to display all chemicals, calculate a pressure, and display a wanted property | Base Chemical Database Test | pass |  | Passed
Requirement | Test for ability to add stock and remove stock, that non-database chemicals cant be added, and that the stock calculates properly | Stockroom Test | pass |  | Passed
Requirement | Test for ability to add chemicals and then add stock of those chemicals and remove them | Combined Test | pass |  | Passed
Note on A51: Establish traceability between the tests and requirements.
Note on B51: Defines observable tests that have quantifiable resutls.
Note on D51: Specifies the result that that the test is anticipated to produce.
Note on F51: Defines the result of running the test in relation to the expected result.
Note on G51: Required whenthe actual result is "Passed with issues"; optional otherwise. An "issue" is a side-effect that is not part of the specified test.

## Map (hidden)
Sceneario-Component Map
X
Component Names:
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Architecture
Architecture
Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components. | Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components.
Standards
| Start date: | 2000-01-01
| End date: | 2010-01-01
| Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
| Defect Types: | Documentation
Syntax
Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
| Y/N: | Yes
No
| Component Types: | Calculation
Data
I/O
Logic
| Design Approaches: | Object-oriented
Functional
| Sizes: | VS
S
M
L
VL
| Duration: | LOCe x T
LOCa x T
Productivity
1 | Component Name: | chem
| Design Approach: | Object-oriented
| Parent Component: | chemicalDatabase
Attributes (optional):
| Component Type: | Data
Collaborators:
| Operations: | hold data for a single chemical
2 | Component Name: | chemicalDatabase
| Design Approach: | Object-oriented
Parent Component:
Attributes (optional):
| Component Type: | I/O
Collaborators:
| Operations: | hold database and functions
3 | Component Name: | stock
| Design Approach: | Object-oriented
| Parent Component: | stockRoom
Attributes (optional):
| Component Type: | Data
Collaborators:
| Operations: | hold data for a single stock of a chemical
4 | Component Name: | stockRoom
| Design Approach: | Object-oriented
Parent Component:
Attributes (optional):
| Component Type: | I/O
Collaborators:
| Operations: | hold info and show info for chemicals in stockroom
5 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
6 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
7 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
8 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
9 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
10 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Note on B43: Identifying name for this design class or function.
Note on B44: Indicate if this design component will follow an object-oriented approach or a functional approach.
Note on B45: Superclass of this design component. Leave blank if no superclass.
Note on B46: Attributes (e.g., public fields, public constants) associated with this design component. OPTIONAL
Note on B47: Standard category of the design component.
Note on B48: List components that this component calls upon to fulfill its purpose.
Note on B49: Description of the operations of this design component. If your are taking an object-oriented approach, list the methods associated with this object in the "operation" column. If you are taking a functional approach, list the component name in the "operation" column. Note: an object-oriented approach may result in zero or more operations; a functional approach will have only one operation listed.

## Estimation (hidden)
Size Estimate
Constants |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 45261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 45252 | 0 | 0 | AM | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 45253 | 1 | 5 | PM | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review | Examine test code for risk mitigation |  | F | 0.5 | 45254 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration test | End-to-end test of components to date |  |  |  | 45255 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Repattern | Restructure external design |  |  |  | 45256 | 4 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Postmortem | Capture post-development statistics |  |  |  | 45257 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sandbox | Prove ideas, try concepts |  |  |  | 45258 | 6 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 45259 | 7 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 45260 | 8 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 45261 | 9 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 45262 | 10 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 45263 | 11 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 45264 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 45265 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 45266 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 45267 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 45268 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 45269 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 45270 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 45271 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 45272 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 45273 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Y/N: | Yes |  |  | Passed | 0 | 45274 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| No |  |  | Passed with issues | 0 | 45275 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 45276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Calculation |  |  | Not tested | New | 45277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data |  |  | Not applicable | Reusable | 45278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I/O |  |  |  |  | 45279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logic |  |  |  |  | 45280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 45281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Estimated | [10 empty] | Actual
|  |  | Changes to existing code | [5 empty] | New code |  |  |  |  | Changes to existing code | [5 empty] | New code
Component | Type | Relative Size | Base LOC count | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCr) |  | Base LOC count | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCa) | Is this component reusable?
chem | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
chemicalDatabase | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
stock | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
stockRoom | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
Totals |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Size Calculation
0
0
0
|  | 0 | Low
Effort Calculation
#DIV/0!
3.6658
0
0
0
|  | 0 | Low
Estimation: | LOCr= |  | 0
| LOCp= | [12 empty] | Actual: | LOCa= | 0
Ep=
Rationale for override:

## ArcEstimation (hidden)
Size Estimate
Standards
Start date: | 2000-01-01 |  |  | Grades: | AA
End date: | 2020-01-01 |  |  |  | A
Phases: | Planning |  |  |  | AB
| Architecture |  |  |  | B
| Construction |  |  |  | BC
| Refactoring |  |  |  | C
| Integration Test |  |  |  | CD
| Review |  |  |  | D
| Sandbox |  |  |  | F
Postmortem
Defect Types: | Documentation
| Build |  |  | Type | Event
| Product syntax |  |  |  | Response
| Product logic |  |  | Origin | Test Component
| Product interface |  |  |  | Blackbox
| Product checking |  |  |  | User
| Test syntax |  |  |  | External Component (specify)
| Test logic |  |  | Op Spec type | User
| Test interface |  |  |  | Interface
Test checking
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Metaphysics: | Object-oriented
Functional
Sizes: | VS
S
M
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
| Estimated |  |  |  |  | Actual
Base Components | Base LOC | Deleted LOC | Modified LOC | Added LOC |  | Base LOC | Deleted LOC | Modified LOC | Added LOC
Totals | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Estimated |  |  |  |  | Actual
New Components | Method Count | LOCr | Reuseable? |  |  | Method Count | LOCa | Reusable?
Totals |  | 0 |  |  |  |  | 0
Actual
Reused Parts | LOC
Totals | 0
Size Calculation
#REF!
0
#REF!
|  | 0 | Low
Effort Calculation
#DIV/0!
3.6658
#REF!
#REF!
#REF!
|  | 0 | Low
Estimation | LOCr= |  | 0
| LOCp= |  | 0 |  |  | LOCa= | 0
| Ep= |  | 0
Rationale for override:
Note on G66: Indicate only new methods and LOC that resulted from effort. Do not count items that were previously base code and were refactored into new components.

## Plan
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to record how much production code you plan to write and the amount of time to write it. Record the actual size once the project is complete. The actual time will be calculated from the Time Log. Please note that you are not being evaluated on how close your planned values to your actual values.
Program Size (LOC) |  | Plan | Actual | To Date
Base code LOC count |  | 345 | 345 | 345
Lines deleted from Base |  | 15 | 13 | 13
Lines modified from Base |  | 50 | 46 | 46
Lines added to Base |  | 50 | 64 | 64
Reused lines |  |  |  | 0
New lines of production code |  | 25 | 34 | 435
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 30 | 30 | 2.174%
Architect |  |  | 155 | 155 | 11.23%
Plan project |  |  | 85 | 85 | 6.159%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 735 | 735 | 53.26%
Refactor |  |  | 140 | 140 | 10.14%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 60 | 60 | 4.348%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 120 | 120 | 8.696%
Sandbox |  |  | 55 | 55 | 3.986%
TOTAL |  | 1200 | 1380 | 1380 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 4 | 4 | 80%
Refactor |  |  | 1 | 1 | 20%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 5 | 5 | 100%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 0 | 0 | 0%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 0 | 0 | 0%
Note on C48: Number of lines used from previously-written code
Note on C49: Estimate of the number of lines deleted from previously-written code
Note on C50: Estimated of the number of lines modified from previously-written code
Note on C51: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C52: Count of the number of lines of reused source code
Note on C53: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C56: Number of reusable components that will be reused.
Note on C57: Estimate of the number of previously-delivered components that will be used.
Note on C58: Estimate of the number of new components to be built.
Note on C72: Estimate in minutes how much time you plan to expend on this assignment.

## Iterations (hidden)
Iterations
Standards
Start date: | 2000-01-01
End date: | 2025-01-01
Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
Documentation
Syntax
Defect Types: | Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
|  |  | estimation methods | A
Sizes: | VS |  |  | B
| S |  |  | C
| M |  |  | D
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
Component-Iteration Map
| Component | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7 | Iteration 8 | Iteration 9 | Iteration 10
Base Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
New Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Number of tasks: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Effort: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS
| Iteration Number | Planned Effort (minutes) | Cumulative Planned Effort | Planned Velocity | Cumulative Planned Velocity | Planned Completion Date
| 1 |  | 0 |  | 0
| 2 |  | 0 |  | 0
| 3 |  | 0 |  | 0
| 4 |  | 0 |  | 0
| 5 |  | 0 |  | 0
| 6 |  | 0 |  | 0
| 7 |  | 0 |  | 0
| 8 |  | 0 |  | 0
| 9 |  | 0 |  | 0
| 10 |  | 0 |  | 0
Calendar
| Day # | Date | Available Minutes | Cumulative Minutes | Planned Velocity | Cumulative Planned Velocity
| 1 | due date - 24 |  | 0 |  | 0
| 2 | due date - 23 |  | 0 |  | 0
| 3 | due date - 22 |  | 0 |  | 0
| 4 | due date - 21 |  | 0 |  | 0
| 5 | due date - 20 |  | 0 |  | 0
| 6 | due date - 19 |  | 0 |  | 0
| 7 | due date - 18 |  | 0 |  | 0
| 8 | due date - 17 |  | 0 |  | 0
| 9 | due date - 16 |  | 0 |  | 0
| 10 | due date - 15 |  | 0 |  | 0
| 11 | due date - 14 |  | 0 |  | 0
| 12 | due date - 13 |  | 0 |  | 0
| 13 | due date - 12 |  | 0 |  | 0
| 14 | due date - 11 |  | 0 |  | 0
| 15 | due date - 10 |  | 0 |  | 0
| 16 | due date - 9 |  | 0 |  | 0
| 17 | due date - 8 |  | 0 |  | 0
| 18 | due date - 7 |  | 0 |  | 0
| 19 | due date - 6 |  | 0 |  | 0
| 20 | due date - 5 |  | 0 |  | 0
| 21 | due date - 4 |  | 0 |  | 0
| 22 | due date - 3 |  | 0 |  | 0
| 23 | due date - 2 |  | 0 |  | 0
| 24 | due date - 1 |  | 0 |  | 0
| 25 | due date |  | 0 |  | 0
| 26 | due date + 1 |  | 0 |  | 0
| 27 | due date + 2 |  | 0 |  | 0
| 28 | due date + 3 |  | 0 |  | 0
| 29 | due date + 4 |  | 0 |  | 0
| 30 | due date + 5 |  | 0 |  | 0
| 31 | due date + 6 |  | 0 |  | 0
| 32 | due date + 7 |  | 0 |  | 0
| 33 | due date + 8 |  | 0 |  | 0
| 34 | due date + 9 |  | 0 |  | 0
| 35 | due date + 10 |  | 0 |  | 0
| 36 | due date + 11 |  | 0 |  | 0
| 37 | due date + 12 |  | 0 |  | 0
| 38 | due date + 13 |  | 0 |  | 0
| 39 | due date + 14 |  | 0 |  | 0
| 40 | due date + 15 |  | 0 |  | 0
| 41 | due date + 16 |  | 0 |  | 0
| 42 | due date + 17 |  | 0 |  | 0

## Summary (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to show how much production code you plan to write and the amount of time to write it. Values are extracted from the Estimation tab.
Program Size (LOC) |  | Plan | Actual | To Date
LOC |  | 0 | 0 | 401
LOCa |  |  |  | 0
Lines added to Base |  | 0 |  | 0
Reused lines |  |  |  | 0
New lines of production code |  | 0 |  | 401
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  | 0 | 30 | 30 | 2.174%
Architect |  | 0 | 155 | 155 | 11.23%
Plan project |  | 0 | 85 | 85 | 6.159%
Plan iteration |  | 0 | 0 | 0 | 0%
Construct |  | 0 | 735 | 735 | 53.26%
Refactor |  | 0 | 140 | 140 | 10.14%
Review |  | 0 | 0 | 0 | 0%
Integration test |  | 0 | 60 | 60 | 4.348%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 120 | 120 | 8.696%
Sandbox |  | 0 | 55 | 55 | 3.986%
TOTAL |  | 0 | 1380 | 1380 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 4 | 4 | 80%
Refactor |  |  | 1 | 1 | 20%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 5 | 5 | 100%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 0 | 0 | 0%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 0 | 0 | 0%
Note on C50: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C51: Count of the number of lines of reused source code
Note on C52: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C55: Number of reusable components that will be reused.
Note on C56: Estimate of the number of previously-delivered components that will be used.
Note on C57: Estimate of the number of new components to be built.

## PlanSummary (hidden)
Project Plan Summary
Standards
Start date: | 2000-01-01 |  | Grades: | AA
End date: | 40179 |  |  | A
Phases: | Analysis |  |  | AB
| Architecture |  |  | B
| Planning |  |  | BC
| Construction |  |  | C
| Refactoring |  |  | CD
| Review |  |  | D
| Integration Test |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration | NA
| Build |  |  | 1
| Product syntax |  |  | 2
| Product logic |  |  | 3
| Product interface |  |  | 4
| Product checking |  |  | 5
| Test syntax |  |  | 6
| Test logic |  |  | 7
| Test interface |  |  | 8
| Test checking |  |  | 9
| Bad Smell |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
|  | Plan | Actual | To Date
Program Size (LOC)
Base code LOC count |  | 0 | 0 | 0
Lines deleted from Base |  | 0 | 0 | 0
Lines modified from Base |  | 0 | 0 | 0
Lines added to Base |  | 0 | 0 | 0
Reused lines |  | #REF! | 0 | 0
New lines of production code |  | #REF! | 0 | 401
|  | Plan | Actual | To Date | To Date %
Time In Phase (minutes)
Analyze |  | 0 | 30 | 30 | 25%
Architect |  | 0 | 155 | 155 | 129.2%
Plan project |  | 0 | 85 | 85 | 70.83%
Plan iteration |  | 0 | 0 | 0 | 0%
Construct |  | 0 | 735 | 735 | 612.5%
Refactor |  | 0 | 140 | 140 | 116.7%
Review |  | 0 | 0 | 0 | 0%
Integration test |  | 0 | 60 | 60 | 50%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 120 | 120 | 100%
Sandbox |  | 0 | 55 | 55 | 45.83%
TOTAL |  | 0 | 1380 | 1380 | 1150%
Changes traced to the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 1 | 1
Refactor |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 1 | 1
Changes implemented in the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 0 | 0
Refactor |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 0 | 0

## Change Log
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 45261 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 45252 | 1 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 45253 | 2 | 5
| Review | Examine test code for risk mitigation |  | F | 0.5 | 45254 | 3 | 10
| Integration test | End-to-end test of components to date |  |  |  | 45255 | 4 | 15
| Repattern | Restructure external design |  |  |  | 45256 | 5 | 20
| Postmortem | Capture post-development statistics |  |  |  | 45257 | 6 | 25
| Sandbox | Prove ideas, try concepts |  |  |  | 45258 | 7 | 30
| Previous Project |  |  |  |  | 45259 | 8 | 35
[6 empty] | 45260 | 9 | 40
[6 empty] | 45261 | 10 | 45
[6 empty] | 45262 | 11 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 45263 | 12 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 45264 | 13 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 45265 | 14 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 45266 | 15 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 45267 | 16 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 45268 | 17 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 45269 | 18 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 45270 | 19 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 45271 | 20 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 45272 | 21 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 45273 | 22 | 0
Y/N: | Yes |  |  | Passed | 0 | 45274 | 23 | 0
| No |  |  | Passed with issues | 0 | 45275 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 45276 | 0 | 0
| Calculation |  |  | Not tested | New | 45277 | 0 | 0
| Data |  |  | Not applicable | Reusable | 45278 | 0 | 0
| I/O |  |  |  |  | 45279 | 0 | 0
| Logic |  |  |  |  | 45280 | 0 | 0
[6 empty] | 45281 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0
[6 empty] | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0
Change Log
Use this worksheet to record changes to made to artifacts after the project is underway. Record repairs to defects, as well as changes that result from requirements clarifications/changes.
|  | Change Designation | Description
|  | Requirements Change | Changes to requirements
|  | Requirements Clarification | Clarifications to requirements
|  | Product syntax | Syntax flaws in the deliverable product
|  | Product logic | Logic flaws in the deliverable product
|  | Product interface | Flaws in the interface of a component of the deliverable product
|  | Product checking | Flaws with boundary/type checking within a component of the deliverable product
|  | Test syntax | Syntax flaws in the test code
|  | Test logic | Logic flaws in the test code
|  | Test interface | Flaws in the interface of a component of the test code
|  | Test checking | Flaws with boundary/type checking within a component of the test code
|  | Bad Smell | Refactoring changes (please note the bad smell in the defect description)
Change Number | Date Of Change | Change Type | Activity Where Injected | Iteration Where Injected | Activity Where Removed | Iteration Where Removed | Fix Time | Reference To A Previous Change | Description
1 |  | Product logic | Construct | 2 |  |  | 15 |  | Date cell not working. 11/15/23 pop.back was taking out last value of vector and closing program
2 |  | Product syntax | Construct | 2 |  |  | 25 |  | 11/15/23 wrong value in while statement causing infinite loop
3 |  | Product logic | Construct | 3 |  |  | 30 |  | 11/16/23 cout of a string with spaces not working, changed to getline
4 |  | Product logic | Construct | 4 |  |  | 45 |  | 11/18/23 stock amounts not adding properly, issues when stocks vector is empty
5 |  | Bad Smell | Refactor | 1 |  |  | 20 |  | 11/20/2023 changed menu structure and how data is sent between classes
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75

## Time Log
Constants | [6 empty] | 0
Start date: | 36526 |  | AA |  | Grades: | AA | 1
End date: | 73051 |  | A |  |  | A | 0.95
Phases: | Analyze | 0 | Identifying customer needs |  | AB | 0.9 | 0 | 0
| Architect | 0 | High-level design |  | B | 0.85 | 0 | 0
| Plan project | 0 | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0
| Plan iteration | 0 | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0
| Construct | 0 | Low-level design, coding, unit testing |  | CD | 0.7 | 45252 | 0
| Refactor | 0 | Restructure internal design |  | D | 0.65 | 45253 | 1
| Review | 0 | Examine test code for risk mitigation |  | F | 0.5 | 45254 | 2
| Integration test | 0 | End-to-end test of components to date |  |  |  | 45255 | 3
| Repattern | 0 | Restructure external design |  |  |  | 45256 | 4
| Postmortem | 0 | Capture post-development statistics |  |  |  | 45257 | 5
| Sandbox | 0 | Prove ideas, try concepts |  |  |  | 45258 | 6
Defect Types: | Requirements Change |  | NA |  | Iteration | NA | did not follow
| Requirements Clarification |  | 1 |  |  | 1 | very painful
| Product syntax |  | 2 |  |  | 2 | painful
| Product logic |  | 3 |  |  | 3 | neutral
| Product interface |  | 4 |  |  | 4 | helpful
| Product checking |  | 5 |  |  | 5 | very helpful
| Test syntax |  | 6 |  |  | 6
| Test logic |  | 7 |  |  | 7
| Test interface |  | 8 |  |  | 8
| Test checking |  | 9 |  |  | 9
| Bad Smell |  | 10 |  |  | 10 | 0
Y/N: | Yes |  | Passed |  |  | Passed | 0
| No |  | Passed with issues |  |  | Passed with issues | 0
Proxy Types: | - |  | Failed |  |  | Failed | Base
| Calculation |  | Not tested |  |  | Not tested | New
| Data |  | Not applicable |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS |  | L |  | M | L | VL
upper | -1.5 |  | 1.5 |  | 0.5 | 1.5 | 99999
mid | -2 |  | 1 |  | 0 | 1 | 2
lower | 0 |  | 0.5 |  | -0.5 | 0.5 | 1.5
| 0 |  | 0 |  | 0 | 0
<-- Mandatory
Time Recording Log
Use this worksheet to record the amount of time you spend on each activity. Use the "sandbox" activity to record time spent experimenting with the assignment requirements..
|  | Activity |  | Meaning
|  | Analyze |  | Identifying customer needs
|  | Architect |  | High-level design
|  | Plan project |  | Determine actions/effort for project duration
|  | Plan iteration |  | Determine actions/effort this iteration
|  | Construct |  | Low-level design, coding, unit testing
|  | Refactor |  | Restructure internal design
|  | Review |  | Examine test code for risk mitigation
|  | Integration test |  | End-to-end test of components to date
|  | Repattern |  | Restructure external design
|  | Postmortem |  | Capture post-development statistics
|  | Sandbox |  | Prove ideas, try concepts
| Start Time |  | Stop Time
Date | Hour | Min | Hour | Min | Interrupt | Delta | Activity | Iteration | Comments
2023-10-23 | 12 | 20 | 12 | 50 |  | 30 | Analyze | 1 | initial thoughts and ideas
2023-10-25 | 13 | 10 | 14 | 30 |  | 80 | Architect | 1 | start planning out classes and function details
2023-11-01 | 10 | 30 | 11 | 45 |  | 75 | Architect | 2 | add more detail
2023-11-03 | 11 | 25 | 12 | 50 |  | 85 | Plan project | 1 | organize timeline for finishing project
2023-11-05 | 14 | 0 | 17 | 0 |  | 180 | Construct | 1 | start bulding code
2023-11-15 | 13 | 30 | 14 | 50 |  | 80 | Construct | 2 | continue building code
2023-11-15 | 9 | 30 | 10 | 25 |  | 55 | Sandbox | 1 | learning how to implement desired items
2023-11-16 | 12 | 0 | 14 | 30 |  | 150 | Construct | 3 | continue coding, going back over to find issues at first glance
2023-11-18 | 18 | 30 | 23 | 55 |  | 325 | Construct | 4 | finish up base code
2023-11-20 | 14 | 30 | 16 | 50 |  | 140 | Refactor | 1 | changing structure to fix bugs
2023-11-21 | 9 | 30 | 10 | 30 |  | 60 | Integration test | 1 | test code
2023-11-29 | 12 | 30 | 14 | 30 |  | 120 | Postmortem | 1 | analyze algorithms, calculate big O

## Lessons
Lessons Learned
Problems of Importance
1
2
3
4
5
Proposal for Improvements
1 | add more calculation features to the database
2 | add prices and automatic reordering of chemicals in stock
3 | be able to output reports in text files with information about a desired list of chemicals
4
5
Notes and Comments
1
2
3
4
5

## Source (hidden)
Source Code
Paste production source code here. (1) copy your code to the clipboard, (2) click on the "PASTE ME" cell (not the entire row), (3) paste. Do not paste test code.
PASTE ME

## Constants (hidden)
Constants | [5 empty] | 0
Start date: | 2000-01-01 |  |  | Grades: | AA | 100% |  |  | 2023-12-01
End date: | 2100-01-01 |  |  |  | A | 95%
Phases: | Analyze |  | Identifying customer needs |  | AB | 90%
| Architect |  | High-level design |  | B | 85%
| Plan project |  | Determine actions/effort for project duration |  | BC | 80%
| Plan iteration |  | Determine actions/effort this iteration |  | C | 75%
| Construct |  | Low-level design, coding, unit testing |  | CD | 70% | 2023-11-22 | 0 | 0 | AM
| Refactor |  | Restructure internal design |  | D | 65% | 2023-11-23 | 1 | 5 | PM
| Review |  | Examine test code for risk mitigation |  | F | 50% | 2023-11-24 | 2 | 10
| Integration test |  | End-to-end test of components to date |  |  |  | 2023-11-25 | 3 | 15
| Repattern |  | Restructure external design |  |  |  | 2023-11-26 | 4 | 20
| Postmortem |  | Capture post-development statistics |  |  |  | 2023-11-27 | 5 | 25
| Sandbox |  | Prove ideas, try concepts |  |  |  | 2023-11-28 | 6 | 30
[7 empty] | 2023-11-29 | 7 | 35
[7 empty] | 2023-11-30 | 8 | 40
[7 empty] | 2023-12-01 | 9 | 45
[7 empty] | 2023-12-02 | 10 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow |  | 2023-12-03 | 11 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful |  | 2023-12-04 | 12
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful |  | 2023-12-05 | 13
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral |  | 2023-12-06 | 14
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful |  | 2023-12-07 | 15
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful |  | 2023-12-08 | 16
| Test syntax | Syntax flaws in the test code |  | 6 |  |  | 2023-12-09 | 17
| Test logic | Logic flaws in the test code |  | 7 |  |  | 2023-12-10 | 18
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  |  | 2023-12-11 | 19
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  |  | 2023-12-12 | 20
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 |  |  | 2023-12-13 | 21
Y/N: | Yes |  |  | Passed |  |  | 2023-12-14 | 22
| No |  |  | Passed with issues |  |  | 2023-12-15 | 23
Proxy Types: | - |  |  | Failed | Base |  | 2023-12-16
| Calculation |  |  | Not tested | New |  | 2023-12-17
| Data |  |  | Not applicable | Reusable |  | 2023-12-18
| I/O | [5 empty] | 2023-12-19
| Logic | [5 empty] | 2023-12-20
2023-12-21
Sizes: | VS | S | M | L | VL | VS
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 | -1 | 0 | 1 | 2 | M
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L
VL
<-- Mandatory |  | ✔